MAOS

Full Roadmap & Sprint Consistency Audit

v1.0

| Field | Value |
| --- | --- |
| Document | MAOS Full Roadmap & Sprint Consistency Audit v1.0 |
| Audit Date | 2026-06-11 |
| Auditor | Architecture Review |
| Scope | Phase 15 Roadmap vs EP Sprint Series — Sprints 0–13 |
| Documents Reviewed | Phase 15 Roadmap, Phase 14 Architecture, All EP Sprints 0–11, Block 1 Close-Out, Sprint 12 & 13 partial artifacts |
| Sprint 12 Status | BLOCKED — pending this audit and amendment |
| Final Verdict | C — ROADMAP AMENDMENT REQUIRED BEFORE SPRINT 12 |
| Amendment | MAOS_EP_Active_Roadmap_Amendment_v1.0.md — issued concurrently |

# 1. Executive Summary

The MAOS project operates under two distinct sprint sequences that share a common origin but diverge permanently at Sprint 10. Phase 15 planned a 13-sprint linear MVP path ending at production launch. The Execution Package (EP) Series followed Phase 15 exactly for Sprints 0–9, then made a deliberate architectural decision to expand the MVP scope, introduce a Block governance layer, and redirect the sprint sequence toward deeper feature completeness.

As of Sprint 11, the EP Series is the only active, living roadmap. Sprint 11 was a hybrid sprint that merged EP feature delivery (Reporting, Search, Data Governance) with Phase 15 Sprint 11 scope (MVP QA, UAT, Security Hardening). Sprint 12 and Sprint 13 partial artifacts already exist in the repository, following Phase 15's RC and Launch paths respectively.

Sprint 12 formal EP Execution Package generation was blocked pending this audit and the concurrent EP Active Roadmap Amendment v1.0. Both documents must be saved before Sprint 12 packaging may proceed.

| Finding | Verdict |
| --- | --- |
| Phase 15 Sprints 0–9 | Fully aligned with EP Series — valid reference |
| Phase 15 Sprints 10–13 | Superseded — formally retired by Amendment v1.0 |
| EP Series | Sole active roadmap from Sprint 0 onwards |
| Sprint 11 hybrid scope | Confirmed — EP S11 features + Phase 15 S11 QA/UAT merged |
| Sprint 12 artifacts | Exist (partial) — formal EP packaging authorized post-amendment |
| Sprint 13 artifacts | Exist (partial) — blocked until Sprint 12 RC gates pass |
| GAP-01 MVP Regression | CLOSED — resolved in Sprint 11 |
| GAP-02 RC Hardening | IN PROGRESS — Sprint 12 |
| GAP-03 Production Launch | BLOCKED — awaits Sprint 12 completion |
| Sprint 12 generation | BLOCKED until amendment + audit saved |
| Final Verdict | C — ROADMAP AMENDMENT REQUIRED BEFORE SPRINT 12 |

# 2. Phase 15 Sprint Sequence Table

The following table shows the original Phase 15 Implementation Roadmap v1.0 sprint sequence as planned. Sprints marked RETIRED have been formally superseded by the EP Series.

| Sprint | Title | Milestone | Goal Summary | Status |
| --- | --- | --- | --- | --- |
| S0 | Setup & Architecture Readiness | M0 | Repo, ADRs, CI, environments, security baseline | Valid |
| S1 | Identity, Tenants, Permissions, Audit Foundation | M1 | Auth, invites, sessions, RBAC, audit logging | Valid |
| S2 | Workspace Shell, Roles UI, Basic Navigation | M2 | Role-aware shell, navigation, RTL/LTR | Valid |
| S3 | Projects, Tasks, Subtasks Core | M3 | Project/task delivery core | Valid |
| S4 | Client Portal Foundation | M4 | Client-safe portal, client scoping | Valid |
| S5 | CRM Basic + Collaboration Foundation | M5/M6 | CRM pipeline + collaboration channel model | Valid |
| S6 | Files, File Versioning, Approvals | M6 | Storage, signed URLs, approval workflow | Valid |
| S7 | Chat + Notifications + Realtime | M6 | Internal + client chat, notifications, realtime | Valid (offset) |
| S8 | Voice Notes + Voice-To-Task Basic | M7 | Voice capture, transcription, AI task draft | Valid (offset) |
| S9 | Finance Basic | M8 | Invoices, partial payments, revenue tracking | Valid |
| S10 | Dashboards & Reports Basic | M9 | Role-safe dashboards, basic reports | RETIRED |
| S11 | MVP QA, UAT, Security Hardening | M10 | Full regression, UAT, hardening, RC prep | RETIRED (merged into EP S11) |
| S12 | MVP Release Candidate | M10/M11 | Scope freeze, RC hardening, launch readiness | RETIRED (superseded by EP S12) |
| S13 | MVP Launch | M11 | Production rollout to pilot tenant | RETIRED (superseded by EP S13) |

# 3. Execution Package Sprint Sequence Table

The following table shows the actual sprint sequence created in the Execution Package Series. This is the sole authoritative sequence.

| Sprint | Title | Block | Goal Summary | Status |
| --- | --- | --- | --- | --- |
| S0 | Setup & Architecture Readiness | Foundation | Repo, standards, CI, environments | Complete |
| S1 | Identity, Auth, Tenants, RBAC, Audit Foundation | Foundation | Tenant model, invites, sessions, RBAC, audit | Complete |
| S2 | Workspace Shell & Navigation | Foundation | Role-aware shell, routing, RTL/LTR, localization | Complete |
| S3 | Projects, Tasks, Subtasks Core | Foundation | Project/task/subtask delivery, assignments, permissions | Complete |
| S4 | Client Portal Foundation | Foundation | Client-scoped portal, client own-data rules | Complete |
| S5 | CRM Basic + Collaboration Foundation | Foundation | CRM pipeline, leads, opportunities, internal notes | Complete |
| S6 | Files, File Versioning, Approvals | Foundation | File upload, versions, signed URLs, approvals | Complete |
| S7 | Client Portal Visibility & Approval UX | Block 1 | Client-facing portal, client approval flows | Complete |
| S8 | Chat, Comments, Mentions & Realtime | Block 1 | Internal + client chat, notifications, realtime | Complete |
| S9 | Voice Notes, Transcription & Voice-to-Task | Block 1 | Voice capture, AI transcription, task draft | Complete — Block 1 Closed |
| S10 | Finance Portal, Client Invoices & Payment Visibility | Block 2 | Finance portal, invoice lifecycle, client payment view | Complete |
| S11 | Reporting, Search, Data Governance & MVP QA/UAT | Block 2 | Reporting, search, governance, QA/UAT/security hardening | Complete |
| S12 | MVP RC Stabilization & RC Governance | Block 2 | RC gates, UAT evidence, security sign-off, performance | Next — authorized |
| S13 | MVP Production Launch | Block 3 | Production rollout, handover, monitoring | Blocked until S12 complete |

# 4. Divergence Table

This table shows where and why the EP Series diverged from Phase 15, sprint by sprint.

| Sprint | Phase 15 Plan | EP Actual | Divergence Type | Root Cause |
| --- | --- | --- | --- | --- |
| S0 | Setup & Architecture Readiness | Setup & Architecture Readiness | None | Aligned |
| S1 | Identity, Tenants, Permissions, Audit | Identity, Auth, Tenants, RBAC, Audit | Cosmetic | EP added detail; same scope |
| S2 | Workspace Shell, Roles UI, Navigation | Workspace Shell & Navigation | Cosmetic | Same scope, different naming |
| S3 | Projects, Tasks, Subtasks Core | Projects, Tasks, Subtasks Core | None | Aligned |
| S4 | Client Portal Foundation | Client Portal Foundation | None | Aligned |
| S5 | CRM Basic + Collaboration Foundation | CRM Basic + Collaboration Foundation | None | Aligned |
| S6 | Files, File Versioning, Approvals | Files, File Versioning, Approvals | None | Aligned |
| S7 | Chat + Notifications + Realtime | Client Portal Visibility & Approval UX | Content Shift | EP gave Client Portal UX its own sprint; one-sprint cascade |
| S8 | Voice Notes + Voice-To-Task | Chat, Comments, Mentions & Realtime | Number Shift | EP S8 = P15 S7 content; offset from S7 split |
| S9 | Finance Basic | Voice Notes, Transcription & Voice-to-Task | Number Shift | EP S9 = P15 S8 content; offset continues |
| S10 | Dashboards & Reports Basic | Finance Portal, Client Invoices & Payment | FULL DIVERGENCE | EP expanded Finance into dedicated portal sprint |
| S11 | MVP QA, UAT, Security Hardening | Reporting + Search + Governance + QA/UAT | HYBRID MERGE | EP merged Phase 15 S11 QA scope into EP S11 feature sprint |
| S12 | MVP Release Candidate | MVP RC Stabilization & RC Governance | Path Convergence | EP Sprint 12 adopts Phase 15 RC path; artifacts exist, formal package pending |
| S13 | MVP Launch | MVP Production Launch | Path Convergence | EP Sprint 13 adopts Phase 15 Launch path; artifacts exist, formal package pending |

# 5. Already Completed Features Matrix (Sprints 0–11)

All features delivered and confirmed as complete across EP Sprints 0–11.

| Domain | Feature | Sprint | Status |
| --- | --- | --- | --- |
| Infrastructure | Repo structure, ADRs, CI baseline, environment plan | S0 | Done |
| Identity | Tenant model, user model, invite-only auth, sessions, devices | S1 | Done |
| Identity | RBAC foundation, PermissionGuard, audit event baseline | S1 | Done |
| UI Shell | Workspace shell, role-aware navigation, RTL/LTR, localization | S2 | Done |
| Projects | Project, Task, Subtask CRUD, assignments, status, priority | S3 | Done |
| Client Portal | Client scoping, client-visible project/task routes | S4 | Done |
| CRM | Leads, Opportunities, Meetings, Follow-ups | S5 | Done |
| Collaboration | Internal notes foundation | S5 | Done |
| Files | File upload, versioning, signed URLs, approvals | S6 | Done |
| Client Portal | Client approval UX, client portal visibility rules | S7 | Done |
| Chat | Internal + client chat, channel membership, notifications | S8 | Done |
| Realtime | WebSocket gateway placeholder, realtime subscription foundation | S8 | Done |
| Voice | Voice note recording, transcription, AI task draft, voice-to-task | S9 | Done |
| Finance | Invoice lifecycle, payment tracking, partial payments | S10 | Done |
| Finance | Client invoice + payment visibility, overdue detection | S10 | Done |
| Finance | Owner-only finance enforcement, finance audit events | S10 | Done |
| Reporting | Owner reporting dashboard, 9 entity report views | S11 | Done |
| Reporting | Finance report placeholder, audit report, activity report | S11 | Done |
| Search | Global search (SearchIndex, permission-aware, client-safe) | S11 | Done |
| Governance | Soft-delete governance, archive policy, retention policy (inactive) | S11 | Done |
| Governance | Export request placeholder, governance audit logging | S11 | Done |
| QA/UAT | MVP regression checklist (Sprints 1–10) | S11 | Done |
| Security | Security hardening checklist, tenant isolation, permission guard | S11 | Done |
| UAT | UAT scenarios (Owner, Manager, Employee, Client), UAT evidence template | S11 | Done |
| Known Issues | Known issue register, KI-001/002/003 disposition | S11 | Done |
| Release Readiness | Release readiness checklist — all gates Ready | S11 | Done |

# 6. Missing / Not Yet Covered Features Matrix

Features planned across all MAOS specifications that have not yet been delivered. All items below are formally deferred to Block 3 or later.

| Feature | Source | Target Sprint | Block | Priority |
| --- | --- | --- | --- | --- |
| Finance BI Reports (full analytics) | S11 deferred / Phase 15 M9 | Sprint 14 | Block 3 | P0 |
| Invoice PDF Generation | S10 placeholder | Sprint 14 | Block 3 | P0 |
| Export Execution (CSV/PDF/JSON delivery) | S11 placeholder | Sprint 14 | Block 3 | P0 |
| Automated Archive Enforcement | S11 deferred | Sprint 14 | Block 3 | P1 |
| Soft-Delete Recovery | S11 deferred | Sprint 14 | Block 3 | P1 |
| SearchIndex Background Cleanup | S11 R11-06 | Sprint 14 | Block 3 | P1 |
| SMTP Email Delivery (CS-01) | Deferred since S8 | Sprint 15 | Block 3 | P0 |
| Report Scheduling + Email Delivery | S11 deferred | Sprint 15 | Block 3 | P1 |
| Retention Policy Enforcement | S11 deferred | Sprint 15 | Block 3 | P1 |
| Automation Engine & Workflow Rules | Phase 10 spec | Sprint 16 | Block 3 | P1 |
| Presence Indicators (CS-02) | Deferred since S9 | Sprint 17+ | Block 3 | P2 |
| Typing Indicators (CS-03) | Deferred since S8 | Sprint 17+ | Block 3 | P2 |
| Threaded Chat Replies | S8 deferred | Sprint 17+ | Block 3 | P2 |
| Full-Text Search Engine (Elasticsearch) | S11 deferred | Sprint 17+ | Block 3 | P2 |
| Voice Transcript Full-Text Search | S11 deferred | Sprint 17+ | Block 3 | P2 |
| Finance BI Advanced Dashboards | S11 deferred | Sprint 14 | Block 3 | P0 |
| GDPR Erasure / Data Purge | S11 deferred | Sprint 17+ | Block 3 | P3 |
| Real-Time Reporting | S11 deferred | Sprint 17+ | Block 3 | P3 |
| AI-Generated Report Summaries | S11 deferred | Sprint 17+ | Block 3 | P3 |
| Payroll Reports | S11 deferred | Sprint 17+ | Block 3 | P3 |
| RC Hardening (full) | Phase 15 S12 | Sprint 12 | Block 2 | P0 |
| Production Launch | Phase 15 S13 | Sprint 13 | Block 3 | P0 |

# 7. Duplicated or Misplaced Features Matrix

Assessment of whether any features were duplicated, misplaced, or accidentally assigned to the wrong sprint.

| Feature | Phase 15 Assigned | EP Assigned | Finding |
| --- | --- | --- | --- |
| Finance Basic | S9 | S9 | Aligned — no issue |
| Finance Portal / Client Views | (not in Phase 15 separately) | S10 | EP expansion — intentional, no duplicate |
| Dashboards & Reports Basic | S10 | S11 (expanded) | Phase 15 S10 scope absorbed into EP S11 and expanded — supersession, not duplicate |
| Client Portal foundation | S4 | S4 + S7 | Phase 15 S4 split into EP S4 (foundation) + EP S7 (UX) — intentional, no duplicate |
| Chat + Notifications | S7 (Phase 15) | S8 (EP) | One-sprint offset due to S7 split; content matches, not duplicated |
| Voice Notes | S8 (Phase 15) | S9 (EP) | One-sprint offset; content matches, not duplicated |
| MVP QA / UAT / Security Hardening | Phase 15 S11 | EP S11 (hybrid) | Merged into EP S11 — not duplicated, intentional hybrid |
| MVP Release Candidate | Phase 15 S12 | EP S12 | EP Sprint 12 RC path converges with Phase 15 S12 — no duplication |
| MVP Launch | Phase 15 S13 | EP S13 | EP Sprint 13 converges with Phase 15 S13 — no duplication |
| Search | Not in Phase 15 MVP | S11 (EP) | EP scope expansion — not a duplicate |
| Data Governance | Not in Phase 15 MVP | S11 (EP) | EP scope expansion — not a duplicate |

Verdict: No features are duplicated. All apparent conflicts are intentional scope expansions or one-sprint offsets caused by the EP Sprint 7 client portal split.

# 8. Deferred Scope Register

Formal register of all deferred scope items. CS-series = collaboration deferrals from Block 1. D-series = feature deferrals from Block 2.

| ID | Feature | From Sprint | Target Sprint | Block | Status |
| --- | --- | --- | --- | --- | --- |
| CS-01 | SMTP Email Delivery | S8 → S11 | Sprint 15 | Block 3 | Tracked |
| CS-02 | Presence Indicators | S9 | Sprint 17+ | Block 3 | Tracked |
| CS-03 | Typing Indicators | S8 | Sprint 17+ | Block 3 | Tracked |
| D-01 | Threaded Chat Replies | S8 | Sprint 17+ | Block 3 | Tracked |
| D-02 | Finance BI Reports (Full) | S11 | Sprint 14 | Block 3 | Tracked |
| D-03 | Invoice PDF Generation | S10 | Sprint 14 | Block 3 | Tracked |
| D-04 | Export Execution (File Delivery) | S11 | Sprint 14 | Block 3 | Tracked |
| D-05 | Automated Archive Enforcement | S11 | Sprint 14 | Block 3 | Tracked |
| D-06 | Retention Policy Enforcement | S11 | Sprint 15 | Block 3 | Tracked |
| D-07 | Soft-Delete Recovery | S11 | Sprint 14 | Block 3 | Tracked |
| D-08 | Full-Text Search Engine | S11 | Sprint 17+ | Block 3 | Tracked |
| D-09 | Voice Transcript Search | S11 | Sprint 17+ | Block 3 | Tracked |
| D-10 | Report Scheduling + Email | S11 | Sprint 15 | Block 3 | Tracked |
| D-11 | Manager Reporting Access | S11 | Sprint 14 | Block 3 | Tracked |
| D-12 | Real-Time Reporting | S11 | Sprint 17+ | Block 3 | Tracked |
| D-13 | GDPR Erasure / Data Purge | S11 | Sprint 17+ | Block 3 | Tracked |
| D-14 | Payroll Reports | S11 | Sprint 17+ | Block 3 | Tracked |
| D-15 | AI-Generated Report Summaries | S11 | Sprint 17+ | Block 3 | Tracked |
| D-16 | Automation Engine & Workflow Rules | Phase 10 spec | Sprint 16 | Block 3 | Tracked |
| GAP-01 | MVP Regression / UAT | Phase 15 S11 | Resolved in S11 | Block 2 | CLOSED |
| GAP-02 | RC Hardening | Phase 15 S12 | Sprint 12 | Block 2 | In Progress |
| GAP-03 | Production Launch | Phase 15 S13 | Sprint 13 | Block 3 | Blocked (S12 gate) |

CS-01, CS-02, CS-03 are all properly documented with target sprints. No action required before Sprint 12.

# 9. Block Structure Review

| Block | Sprints | Theme | Status | Close-Out |
| --- | --- | --- | --- | --- |
| Foundation (Pre-Block) | S0–S6 | Architecture, identity, core workspace, CRM, files | All complete | No formal close-out (no block name) |
| Block 1 — Collaboration Layer | S7, S8, S9 | Client Portal Visibility, Chat/Realtime, Voice Notes | CLOSED | Block 1 Close-Out Review v1.0 issued |
| Block 2 — Finance & Reporting + RC | S10, S11, S12 | Finance Portal, Reporting/Search/Governance, RC Stabilization | IN PROGRESS — S10 Done, S11 Done, S12 Next | To be issued after Sprint 12 RC gates pass |
| Block 3 — Post-MVP Enhancements | S13+ | Launch, Finance BI, Invoice PDF, Export, SMTP, Automation, etc. | Not started | Not defined |

### Block 2 Clarification

Block 2 was originally defined as "Finance & Reporting Foundation (Sprints 10–12)." Sprint 11 expanded to absorb Phase 15's QA/UAT scope. Sprint 12 became the RC stabilization sprint rather than a Finance BI feature sprint. The Finance BI/Invoice PDF/Export scope originally planned for EP Sprint 12 has been deferred to Block 3 (Sprint 14).

### Block 3 High-Level Definition

Block 3 covers post-MVP-v1 feature delivery. Defined at sprint-level:

| Sprint | Theme | Key Scope |
| --- | --- | --- |
| 13 | MVP Production Launch | Production rollout, 50-user load gate, monitoring, handover |
| 14 | Finance BI & Export Foundation | Finance BI reports, Invoice PDF, Export execution, Archive enforcement, Soft-delete recovery |
| 15 | Notifications & Delivery | SMTP email (CS-01), Report scheduling, Retention enforcement |
| 16 | Automation Engine | Workflow rules, scheduled actions (Phase 10 spec) |
| 17+ | Advanced Capabilities | Presence (CS-02), Typing (CS-03), Threaded replies, Full-text search, Advanced AI |

# 10. Correct Active Roadmap Recommendation

| Criterion | Phase 15 | EP Series |
| --- | --- | --- |
| Sprints 0–9 | Source of truth | Followed faithfully |
| Sprint 7 EP content | Phase 15 S7 = Chat | EP S7 = Client Portal UX — intentional split |
| Sprint 8–9 offset | One sprint behind EP | Intentional cascade from S7 split |
| Sprint 10 | Dashboards & Reports | Finance Portal — permanent break |
| Sprint 11 | MVP QA/UAT | Reporting + Search + Governance + QA/UAT (hybrid) |
| Sprint 12 | MVP Release Candidate | RC Stabilization (partial artifacts exist; EP packaging pending) |
| Sprint 13 | MVP Launch | Production Launch (partial artifacts exist; EP packaging pending) |
| Block structure | Does not exist in Phase 15 | Block 1 Closed, Block 2 In Progress, Block 3 Defined |
| Deferred scope tracking | Not tracked | Formally tracked per sprint |
| Live implementation | No | Yes — all EPs are implementation contracts |
| Scope depth | MVP-lean planning | Production-quality specification |

Recommendation: The EP Series is the sole active roadmap from Sprint 0 onwards. Phase 15 Sprints 0–9 remain valid reference material. Phase 15 Sprints 10–13 are formally retired by Amendment v1.0.

# 11. Correct Next Sprint Recommendation

### Sprint 12: MVP Release Candidate Stabilization & RC Governance

Sprint 12 is Block 2's final sprint. It formalizes the RC artifacts that already exist in docs/sprint-12/ into a complete EP Execution Package.

| Component | Source | Status |
| --- | --- | --- |
| Release candidate checklist | docs/sprint-12/release-candidate-checklist.md | Exists |
| Final MVP validation matrix | docs/sprint-12/final-mvp-validation-matrix.md | Exists |
| UAT evidence template | docs/sprint-12/uat-evidence-template.md | Exists |
| RC version manifest (RC-0.1.0) | docs/sprint-12/rc-version-manifest.md | Exists |
| Security sign-off checklist | docs/sprint-12/security-signoff-checklist.md | Exists |
| Performance & load readiness plan | docs/sprint-12/performance-load-readiness-plan.md | Exists |
| Environment readiness checklist | docs/sprint-12/environment-readiness-checklist.md | Exists |
| Deployment readiness checklist | docs/sprint-12/deployment-readiness-checklist.md | Exists |
| Rollback readiness checklist | docs/sprint-12/rollback-readiness-checklist.md | Exists |
| Known issue disposition review | docs/sprint-12/known-issue-disposition-review.md | Exists |
| Final release blocker register | docs/sprint-12/final-release-blocker-register.md | Exists |
| Sprint 12 cover / scope plan | docs/sprint-12/ (missing) | REQUIRED |
| MAOS_Sprint12_Execution_Package_v1.0.docx | docs/sprint-12/ (missing) | REQUIRED |
| Block 2 Close-Out Review v1.0 | docs/ (missing) | REQUIRED after S12 RC gates pass |

Sprint 12 is NOT: Automation Engine (no Block 2 basis). Sprint 12 is NOT: MVP launch (precedes Sprint 13). Sprint 12 IS: the formal RC stabilization sprint that closes Block 2 and gates Sprint 13.

# 12. Risks if Continuing Without Fixing Roadmap

| # | Risk | Severity | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | Sprint 12 built without formal EP cover — content drift | High | Sprint 12 EP may contradict existing artifacts | Amendment v1.0 + this audit define Sprint 12 scope |
| R-02 | Phase 15 Sprint 12 ("MVP RC") still referenced as official — confusion about readiness | High | Team may treat Sprint 12 as last sprint before launch incorrectly | Amendment v1.0 formally retires Phase 15 S12 |
| R-03 | GAP-01/02/03 had no assigned sprint — launch date unknown | Critical | No production launch path in EP series | Amendment v1.0 assigns all three gaps |
| R-04 | Block 3 undefined — no roadmap beyond Sprint 12 | High | Work after Sprint 12 has no planning foundation | Block 3 defined in Amendment v1.0 |
| R-05 | Phase 15 Milestone-to-Sprint mapping still shows outdated assignments | Medium | Tools or reports referencing Phase 15 milestones will be wrong | Phase 15 retired by Amendment v1.0 |
| R-06 | Automation Engine (Phase 10 spec) has no assigned sprint in EP | Medium | Feature may be forgotten | Assigned to Sprint 16 in Amendment v1.0 |
| R-07 | Sprint 12/13 partial artifacts lack formal EP Execution Package | High | Incomplete sprint records; no DOCX audit trail | Sprint 12 EP packaging authorized by amendment |

# 13. Required Roadmap Amendments

The following three actions are required before Sprint 12 generation is authorized. Items 1 and 2 are addressed by this audit session.

### Action 1: Issue EP Active Roadmap Amendment v1.0 (COMPLETED)

File: docs/MAOS_EP_Active_Roadmap_Amendment_v1.0.md

Formally retires Phase 15 Sprints 10–13, confirms EP Series as sole active roadmap, defines Block 3, assigns GAP-01/02/03, authorizes Sprint 12 packaging.

### Action 2: Save This Audit Record (COMPLETED by saving this DOCX)

File: docs/MAOS_Full_Roadmap_Sprint_Consistency_Audit_v1.0.docx

Documents all 14 audit sections, Final Verdict C, divergence analysis, and deferred scope register.

### Action 3: Generate Sprint 12 Formal EP Execution Package (NEXT)

Required deliverables:

- docs/sprint-12/sprint-12-s0-cover-scope-plan.md

- docs/sprint-12/MAOS_Sprint12_Execution_Package_v1.0.docx

- docs/MAOS_Block2_CloseOut_Review_v1.0.md (after RC gates pass)

Sprint 13 formal EP packaging remains blocked until Sprint 12 RC gates are passed.

# 14. Final Decision Table

| Question | Answer |
| --- | --- |
| Is Phase 15 still the active roadmap? | No — superseded from Sprint 10 onwards |
| Is the EP Series the active roadmap? | Yes — sole active sequence from Sprint 0 onwards |
| Did Sprints 0–6 follow Phase 15? | Yes — fully aligned |
| Did Sprint 7–9 follow Phase 15? | Partially — one-sprint content offset; no functional gap |
| Did Sprint 10 follow Phase 15? | No — permanent content divergence; EP added finance portal sprint |
| Did Sprint 11 follow Phase 15? | Hybrid — merged EP S11 features with Phase 15 S11 QA/UAT scope |
| Is Sprint 11 confirmed as valid? | Yes — confirmed, approved, Pass result issued |
| Is Block 2 correctly defined? | Yes — Sprints 10, 11, 12; Finance & Reporting + RC |
| Do Sprint 12 artifacts exist? | Yes — partial (RC checklists); formal EP package missing |
| Do Sprint 13 artifacts exist? | Yes — partial (Launch checklists); formal EP package missing |
| Are CS-01, CS-02, CS-03 properly tracked? | Yes — all documented with target sprints |
| What is the correct Sprint 12 title? | MVP Release Candidate Stabilization & RC Governance |
| Is Sprint 12 the Automation Engine? | No — no Block 2 basis; Automation Engine deferred to Sprint 16 |
| Is Sprint 12 Finance BI / Invoice PDF? | No — deferred to Sprint 14 (Block 3) |
| Is Sprint 12 generation authorized? | YES — after amendment + audit are saved |
| Is Sprint 13 generation authorized? | No — blocked until Sprint 12 RC gates pass |
| What is Block 3? | Sprint 13 (Launch) + Sprint 14 (Finance BI/Export) + Sprint 15 (SMTP/Notifications) + Sprint 16 (Automation) + Sprint 17+ (Advanced) |
| GAP-01 MVP Regression | CLOSED — resolved in Sprint 11 |
| GAP-02 RC Hardening | IN PROGRESS — Sprint 12 |
| GAP-03 Production Launch | BLOCKED — awaits Sprint 12 RC gate pass |
| Safest next action | Generate Sprint 12 EP cover/scope plan incorporating existing RC artifacts |

FINAL VERDICT: C — ROADMAP AMENDMENT REQUIRED BEFORE SPRINT 12

SPRINT 12 GENERATION: BLOCKED — pending this audit and EP Active Roadmap Amendment v1.0

UNBLOCK CONDITION: Both docs saved → Sprint 12 generation AUTHORIZED

## Three Required Actions Before Sprint 12

1. COMPLETED: EP Active Roadmap Amendment v1.0 saved to docs/MAOS_EP_Active_Roadmap_Amendment_v1.0.md

2. COMPLETED (by saving this file): Full Roadmap Audit v1.0 saved to docs/MAOS_Full_Roadmap_Sprint_Consistency_Audit_v1.0.docx

3. NEXT: Generate Sprint 12 — MVP Release Candidate Stabilization & RC Governance — formal EP Execution Package